## Slide 1: Applying Plan-Do-Study-Act (PDSA) Methodology and Using Interim Measurement Cycles: A Preventive Dental Services for Children Example
Christy Hormann, LMSW, CPHQ
Project Manager
May 25, 2016

## Slide 2: Review of Plan-Do-Study-Act
Plan—Investigation and problem framing. Design an intervention and data collection plan. Predict the results.
Do—Testing the intervention.
Study—Evaluate data.
Act—Adopt, Adapt, or Abandon. Determine how to sustain the intervention, if successful.

## Slide 3: PDSA—Plan
Plan Information | 
Plan Name: | XYZ Health Plan
Topic: | Preventive Dental Services for Children
Project Contact Name: | Suzie Quality
Project Contact Title: | Quality Improvement Director
Project Contact Email Address: | squality@xyzhealthplan.com
Project Contact Telephone Number: | 555.123.4567
Intervention Being Tested: | Telephone outreach calls to members
Test Cycle Objective: | Three attempts by telephone will be made to reach eligible members’ parents/guardians to provide information on the importance of an annual preventive dental visit. The plan will provide assistance with scheduling the dental appointment if needed and offer transportation.

## Slide 4: Plan: Intervention Plan
Intervention Plan | 
Date Testing Began: | 10/1/2015
Continued, New, or Revised Intervention | New
Member, Provider, or Health Plan Systems/Process-Level Intervention: | Member-Level Intervention
Who is testing the intervention? | Quality Improvement Department/Member Services Representatives
Where is the test taking place? | Member Services Department
How long is the data collection period? | 90 days
What is the intervention methodology? | Member Services receives a monthly list of eligible members from Enrollment. Member Services Representative contacts the member’s parent/guardian. The representative provides information on the importance of an annual preventive dental visit, provides assistance with scheduling the dental appointment if needed, and offers transportation.
What are the predicted results of this test? | The plan predicts that for the members’ parents/guardians who are reached the intervention will be successful. The plan predicts that it may not be possible to reach all members because of inaccurate or missing contact information. The plan predicts that 80 percent of members can be reached by the intervention. Of those reached, the plan predicts that 75 percent of members will get preventive dental service following receipt of the intervention.

## Slide 5: Plan: Evaluation Plan
How the plan will know the change leads to improvement.
The data elements and sources.
How and when data will be collected.
The team member(s) responsible for collecting the data.

## Slide 6: Evaluation Plan Example—Preventive Dental Services for Children
The plan will know that a change leads to improvement by measuring the number of members who receive telephone outreach and the number of members that completed a dental visit after receiving telephone outreach.
Completed dental visits will be collected from provider offices and claims.
If using claims, the plan should assess how complete claims submissions are within a specified timeframe to determine if claims will be a viable source of data for testing an intervention.

## Slide 7: Evaluation Plan Example—Preventive Dental Services for Children (cont.)
Data on attempted and completed outreach calls will be tracked daily.
Representatives will also track scheduling assistance and transportation provided.
Data on completed dental visits will be collected 30, 60, and 90 days following the call.
The Quality Improvement Department will receive data from Member Services weekly, contact provider offices for confirmation of completed dental visits and complete administrative data collection for dental visit claims.
The Quality Improvement Department will calculate and present the results for the PDSA.

## Slide 8: Do: Testing the Intervention
In the Do stage of the cycle, the test is performed and data are collected. Two types of data can be collected during this stage.
Quantitative (measures amount)
Qualitative (measures quality of something)

## Slide 9: Do: Record-Keeping
Record-Keeping
The tracking of any events and/or activities related to the intervention as they occur.
Keeping a record of challenges and/or confounding factors as they occur throughout the intervention period.

## Slide 10: Study: Intervention Results
The Study stage brings together the predictions made in the Plan stage and the results from testing in the Do stage.

## Slide 11: Study: Intervention Effectiveness
The results of intervention testing.
How the results compared to the prediction.
How the data illustrate that the intervention was effective or ineffective.
Lessons learned.
What the plan will do differently when testing again.

## Slide 12: Study: Intervention Effectiveness (cont.)
Dental visit outreach calls | Total # of members attempted to be reached | Total # of members successfully reached (%) | Completed dental visits for members reached (%)
October 2015 | 85 | 33 (39%) | 20 (61%)
November 2015 | 98 | 41 (42%) | 22 (54%)
December 2015 | 82 | 32 (39%) | 18 (56%)
Total: October– December 2015 | 265 | 106 (40%) | 60 (57%)
Overall, from October through December, 40 percent of members were successfully reached for the intervention.

## Slide 13: Study: Intervention Effectiveness (cont.)
How the results compared to the prediction.
  Prediction: The plan predicted that for the members’ parents/guardians who are reached the intervention will be successful. The plan predicted that it may not be possible to reach all members because of inaccurate or missing contact information. The plan predicted that 80 percent of members could be reached by the intervention. Of those reached, the plan predicted that 75 percent of members would get a preventive dental service following receipt of the intervention.
  Results:
  The results showed 60 percent of the members could not be reached because contact information was inaccurate or missing. Across the three months of testing, the percentage of members receiving preventive dental care following receipt of the intervention was 18 percentage points less than predicted.

## Slide 14: Study: Intervention Effectiveness (cont.)
How the data illustrate that the intervention was effective or ineffective.
  Based on the data, the plan determined that in October, November, and December 2015, 106 total members were reached and educated telephonically during this intervention testing in the first three months.
  The percentage of members who were reached and attended a dental visit was a little higher in October and fairly consistent for November and December.

## Slide 15: Study: Intervention Effectiveness (cont.)
Lesson learned.
A challenge was that 60 percent of members could not be reached due to inaccurate or missing contact information. Without current contact information, the plan was not able to reach the member by telephone.
What the plan will do differently when testing again.
The plan developed an initiative to address this challenge.
  Development of a local Member Contact Repository to store member contact information from a variety of sources throughout the plan.
    Transportation vendor
    Community Care Program
    Primary Care Provider offices

## Slide 16: Act: Adopt-Adapt-Abandon
The plan will decide if the intervention will be adopted, adapted, or abandoned.
Adopted: Select changes to test on a larger scale or develop a plan for sustainability if progressive testing revealed that the intervention should be implemented.
Adapted: Integrate the results of lessons learned during the Study phase into a new test or adapt the test to a new or larger environment/situation.
Abandoned: Discard the change idea and test a different one.

## Slide 17: Act: Adopt-Adapt-Abandon (cont.)
Based on the PDSA results, what would you do?

## Slide 18: Important Considerations
According to the Center for Health Care Strategies, Inc., children in Medicaid who begin preventive dental care by age one year have lifetime dental costs that are nearly 40 percent less than those who start care later.
Despite being entitled to free dental services, fewer than half of the nation’s 32 million Medicaid-enrolled children receive any dental care in a given year.
May 3, 2016, taken from: http://www.chcs.org/resource/advancing-oral-health-through-the-women-infants-and-children-program-a-new-hampshire-pilot-project

## Slide 19: Important Considerations (cont.)
Understanding specific barriers that contribute to oral health inequities is essential to creating effective oral health programs and policies.
May 4, 2016, taken from: http://www.chcs.org/resource/a-framework-for-advancing-oral-health-equity

## Slide 20: PDSA Take-Away
In moving from planning to implementation, PDSA provides a structure for experimental learning to know whether a change has worked or not, and to learn and act upon any new information as a result.
PDSA is a flexible method that can be adapted to support the scale-up of an intervention.

## Slide 21: Final PDSA Take-Away
Failure to properly execute PDSAs can undermine learning efforts.
Making a specific prediction and selecting appropriate measures prior to intervention testing provides a foundation for successful learning through PDSAs.
It is crucial that resource requirements for successful application of PDSA for a given project are well understood by everyone involved, and that the process is well managed.

## Slide 22: Open Discussion
Plans’ experience with dental measure PDSA cycles.
  Successes and challenges.
Questions and answers.