## Slide 1: Utilizing The Plan-Do-Study-Act Process to Maximize PIP Performance – Part 1
Christi Melendez, RN, CPHQ
February 2, 2016

## Slide 2: Plan-Do-Study-Act (PDSA)
Rapid-cycle improvement technique.
Four step model for carrying out change.
Used for small scale intervention testing.
Should be repeated for continuous improvement.

## Slide 3: PDSA Stages
The stages of the PDSA cycle:
Plan—change to be tested.
Do—carry out the test.
Study—analyze data before and after the change and reflect on what was learned.
Act—plan the next change cycle.

## Slide 4: Model for Improvement
The Model for Improvement has three fundamental questions leading to the PDSA cycle.
Model for Improvement, developed by Associates for Process Improvement. From ihi.org

## Slide 5: Testing Interventions using PDSA
Evidence and data
Learning and Improvement
Theories, hunches, and best practices
Breakthrough results
Wide-scale tests of change
Test new conditions
Follow-up tests
Very small-scale test
P
S
D
A

## Slide 6: Why test on a small scale?
Testing on a small scale does not mean small change but refers to the initial scope of the test.
Testing change on a small scale is a way to reduce fear of making a change.
The use of multiple testing cycles allows knowledge to increase as the team progresses from testing to implementing a change, while at the same time minimizing risk.
The team can learn very much from failure. The whole point of performing small scale tests is to minimize the risk from failed tests and maximize the learning with regard to what works.

## Slide 7: Plan
The cycle begins with a plan. This includes setting a goal, predicting the outcome, defining metrics and data collection. In the Plan stage determine:
How the plan will know that the change is an improvement.
The data elements and data sources.
How and when data will be collected.
The team member(s) responsible for collecting data.
How often data will be collected.
A data collection tool (or tools), if applicable (e.g., logs, spreadsheets).
How collected data results will be calculated and displayed (e.g., graph, run chart, narrative).

## Slide 8: Do: Testing Interventions
In the Do stage of the cycle, the test is performed and data are collected. Two types of data should be collected during this stage.
Data that are useful for answering questions in the intervention plan and that can be compared to the prediction.
Data about problems and unexpected occurrences during the test.

## Slide 9: Do: Record-Keeping
The tracking of any events and/or activities related to the intervention as they occur.
Keeping a record of challenges and/or confounding factors as they occur throughout the intervention period.

## Slide 10: Study: Intervention Results
The Study stage brings together predictions made in the Plan stage and results from testing in the Do stage.
This is done by comparing results of the data to the prediction.

## Slide 11: Study: Intervention Effectiveness
How results compared to the prediction.
How data illustrate that the intervention was effective or ineffective.
What were the lessons learned.
What the plan will do differently when testing again.

## Slide 12: Act: Adopt-Adapt-Abandon
Adopt: Select changes to test on a larger scale or develop a plan for sustainability if progressive testing revealed that the intervention should be implemented.
Adapt: Integrate results of lessons learned during the Study phase into a new test or adapt the test to a new or larger environment/situation.
Abandon: Discard the change idea and test a different one.

## Slide 13: PDSA Worksheet for Testing Change Institute for Healthcare Improvement
Describe your first (or next) test of change: | Person responsible | When to be done | Where to be done
Plan
List the tasks needed to set up this test of change: | Person responsible | When to be done | Where to be done
Predict what will happen when the test is carried out: | Measures to determine if prediction succeeds
Do Describe what actually happened when you ran the test.
Study Describe the measured results and how they compared to the predictions.
Act Describe what modifications to the plan will be made for the next cycle from what you learned.

## Slide 14: Plan: Dental PIP Example
Describe your first (or next) test of change: | Person Responsible | When to be done | Where to be done
Send practice-specific “report cards” comparing each provider’s preventive dental visit rate to other in-network dental providers. | Quality and Provider Relations staff | Monthly, beginning March 2016 | 2 high-volume counties with historically low preventive visit rates
Notes: Every goal will require multiple smaller tests of change…

## Slide 15: Plan: Dental PIP Example, cont.
List the tasks needed to set up this test of change | Person Responsible | When to be done | Where to be done
Identify eligible dental provider practices in targeted counties. Generate practice-specific preventive dental visit rates. Develop practice-specific preventive dental visit “report card” template. Generate monthly report cards and mail to dental practices. Follow-up with practices to discuss report card. Track and plot monthly practice-specific and overall preventive dental visit rates. |  |  | 

## Slide 16: Plan: Dental PIP Example, cont.
Predict what will happen when the test is carried out | Measures to determine success
Dental provider practices will be receptive to the report cards and will see value in knowing their rate in comparison to other practices. Dental practices will actively outreach eligible members to schedule preventive service appointments. The monthly dental preventive service rate will be higher among the targeted dental practices than among comparable non-targeted practices. | Qualitative feedback on preventive dental visit report cards provided to provider services staff by dental providers. Report card follow-up survey responses regarding providers’ outreach practices to schedule preventive service appointments. Practice-specific monthly preventive dental visit rates.

## Slide 17: Do – Record Keeping: Dental PIP Example Continued
Intervention Progress Log |  |  | 
Date | Events/Activities Related to Intervention | Successes/Challenges/ Confounding Factors | Plans/Next Steps
3/21/16 | Generate a practice-specific “report card” for each dentist comparing baseline preventive dental visit rate to other network dental providers. | The practice-specific preventive dental visit rates only include those enrollees who have a dental service history. What about eligible enrollees who have not sought any dental services? | Staff will compare enrollment data with dental visit claims to identify enrollees who have not sought any dental service. Other interventions will target enrollee awareness of dental benefit and motivation to seek care.
4/15/16 | Send first monthly report cards to identified dental providers. | Provider services staff has received little feedback from dental providers on helpfulness of report cards. | Staff will follow-up with practices by phone to discuss report card. Provider service reps will include future report cards as part of field visits to provider practices.

## Slide 18: Study: Dental PIP Example
Predictions | Measurement Results
Dental provider practices will be receptive to the report cards and will see value in knowing their rate in comparison to other practices. Dental practices will actively outreach eligible members to schedule preventive service appointments. The monthly dental preventive service rate will be higher among the targeted dental practices than among comparable non-targeted practices. | Minimal feedback was received from the dental practices after the first monthly report cards were mailed out but the feedback received was positive. Low survey response rate; responses received indicated that outreach practices to schedule preventive service appointments vary by practice. After the first monthly report card mailing, practice-specific monthly preventive dental visit rates in the targeted counties were similar to comparable non-targeted counties.

## Slide 19: Act: Dental PIP Example
Measurement results after first monthly report card mailing | Planned intervention modifications based on measurement results
Minimal feedback was received from the dental practices after the first monthly report cards were mailed out but the feedback received was positive. Low survey response rate; responses received indicated that outreach practices to schedule preventive service appointments vary by practice. After the first monthly report card mailing, practice-specific monthly preventive dental visit rates in the targeted counties were similar to comparable non-targeted counties. | Quality and provider relations staff will schedule face-to-face visits with targeted provider practices to discuss the preventive visit report card results and seek feedback on improving usefulness. During the face-to-face visits, the agenda will include a discussion of best practices for improving preventive dental visit appointment adherence. Monthly comparisons of preventive visit rates among targeted and non-targeted practices will continue.

## Slide 20: PDSA: Level of Detail
PDSA is a rapid-cycle, small test of change technique.
Adequate, objective detail should be provided in the PDSA worksheet so the reader understands the test and results and does not have substantial questions.
Several pages of documentation are generally not required for one small test of change using the PDSA worksheet.
If the plan has concerns regarding the level of detail, it should have a colleague who was not involved in the PDSA process review the completed worksheet and provide feedback.

## Slide 21: Open Discussion
Questions and Answers